## Blog
Blog |  |  | Review by Alex
Criteria | What the Result is | What needs to be addressed | Github repo or Description of change | Date of Change
Code readability (only applicable to game) | n/a | N/A | N/A | N/A
Security in Word Press | Currently not secure from SQL Injection and user permissions are not secure. | Find a plugin that will protect from SQL injection. Try to change the user permissions in order to provide security to the site
Maintainability | Easily maintainable as there are only two (active) plugins that affect how the blog works. | Make sure the plugins are working nice together. (Which they are not)
Wordpress Plugins Interactivity | Interaction between Buddy Press Groups and Buddy Press is not working. Groups is trying to give role permissions while Buddy Press is not accepting them. | Look into the documentation of Buddy Press and Buddy Press Groups and make sure they work together
Wordpress Plugins active support | There is active support for Buddy Press and Buddy Press Groups. | N/A
Not needlessly complex | With the many "membership" plugins that were installed, there are still remnants of each plugin. Thus causing the workarounds to be needlessly complex. | See if you can consolidate the number of plugins used and make sure they are working together well. This is causing role permissions to be buggy as well.
Documentation | Currently no documentation besides that provided by the plugin | Provide documentation so that the client can easily maintain their site.
Successful Testing | No testing as of yet | Create test cases and build off of that
Speed | Easy Breezy | N/A
Backups | Namecheap provides automatic backups in the cpanel. | N/A
What to do if website goes down? | Contact the namecheap | N/A
Outstanding Bugs/Glitches | Everyone can create groups, which is caused by role permissions being out of wack. | Role permissions need to be fixed in order to better maintain the permissions of the users
Aesthetic Design | Could be better but not a high priority | Not a priority, but find a theme that supports it
Is responsive to multiple devices | This was found to be responsive on multiple devices of different screen sizes | N/A

## Login
Login |  |  | Review by Akeem
Criteria | What the Result is | What needs to be addressed | Github repo or Description of change | Date of Change
Code readability (only applicable to game)
Security in Word Press
Maintainability
Wordpress Plugins active support
Not needlessly complex
Documentation
Successful Testing
Speed
Backups
What to do if website goes down?
Outstanding Bugs/Glitches
Aesthetic Design
Is responsive to multiple devices

## Cover Pages
Cover Pages |  |  | Review by Brandon
Criteria | What the Result is | What needs to be addressed | Github repo or Description of change | Date of Change
Code readability (only applicable to game)
Security in Word Press
Maintainability
Wordpress Plugins active support
Not needlessly complex
Documentation
Successful Testing
Speed
Backups
What to do if website goes down?
Outstanding Bugs/Glitches
Aesthetic Design
Is responsive to multiple devices

## Map
Map |  |  | Review by Jackson
Criteria | What the Result is | What needs to be addressed | Github repo or Description of change | Date of Change
Code readability (only applicable to game)
Security in Word Press
Maintainability
Wordpress Plugins active support
Not needlessly complex
Documentation
Successful Testing
Speed
Backups
What to do if website goes down?
Outstanding Bugs/Glitches
Aesthetic Design
Is responsive to multiple devices

## Game
Game |  |  | Review by Stanley
Criteria | What the Result is | What needs to be addressed | Github repo or Description of change | Date of Change
Code readability (only applicable to game)
Security in Word Press
Maintainability
Wordpress Plugins active support
Not needlessly complex
Documentation
Successful Testing
Speed
Backups
What to do if website goes down?
Outstanding Bugs/Glitches
Aesthetic Design
Is responsive to multiple devices